## Slide 1: Cisco Dynamic Rev-Proxy Timeline
2017
2017
Today
Aug
Sep
Oct
Nov
Dec
Project Assigned
Cisco Dynamic Rev-Proxy
Aug 29
Requirements & Timeline
Sep 12
Research Begins
Sep 14
Contest/Presentations
Dec 15
40 days
100%
Sep 14 – Sep 26
Research
29 days
50%
Sep 26 – Oct 17
Design
36 days
38%
Oct 17 – Nov 14
Development
150 days
40%
Nov 14 – Nov 27
Testing
18 days
Nov 27 – Dec 15
Presentation Prep
25 days
Dec 15
Presentation
Research
Completed –
Design Begins
Sep 26
Design Completed –
Coding Begins
Oct 17
Prototype
Complete –
Testing Begins
Nov14
Presentation
Prep
Nov 27